## bugs
Bug List
# | Milestone | Reported Date | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce
1 | 1 | 2024-10-07 | Yan Naing | P3 | Resolved | Katie | The boar is colliding when it hasn't even touched other moving entities. | The boar should collide only when it touches other moving entities. | The boar is colliding when it hasn't even touched other moving entities. | Try to collide player with the upper part of the boar.
2 | 1 | 2024-10-07 | Linus | P0 | Resolved | Yan Naing | When a player or enemy collides with more than one moving entity, the game crashes. | Any moving entity should be able to collide with any amount of entities at the same time. | When the moving entity collides with 2 or more entities, the game crashes. | Try to get two enemies collide the player.
3 | 1 | 2024-10-09 | Yan Naing | P3 | Resolved | Yan Naing | Once a moving entity collides wih another, it turns red forever, and never back to its original colors. | A moving entity should only turn red momentarily after collision. | Any moving entity is red forever after collision. | Collide the player with any enemy to trigger color change.
4 | 2 | 2024-10-12 | Linus | P4 | Resolved | Carlo | Tabbing in and out of the game is slow | Should be able to tab in and out of the game smoothly with no delays | Use windowed full screen instead of full screen. | Tab in and out of the game.
5 | 2 | 2024-10-30 | Linus | P4 | Resolved | Linus | Arrows shot to the left are rendered backwards | Arrows should be displayed in the direction they are shot. | Arrows in correct orientation as shot. | Try to get archer shoot arrows from left or right.
6 | 2 | 2024-11-01 | Linus | P3 | Resolved | Linus | Arrows go through the tree | Arrows should stick to the tree. | Arrows stick to the tree | Get archer closer to the tree and let it shoot.
7 | 2 | 2024-11-01 | Linus | P3 | Resolved | Linus | Obstacles spawned side by side with same y-position flicker | Obstacles should not flicker under any circumstances | Obstacles do not flicker anymore | Try to spot obstacles (rocks, trees, bushes) and see if they flicker.

## bug_severities
Severity | Description
P0 | crash bug; game crashes and is unrecoverable
P1 | game stopping bug, but no crash; cannot keep playing
P2 | serious, game not working as expected
P3 | annoying, could ship but loss of marks
P4 | annoying or limiting, but could be shipped as-is
P5 | minor or feature that nice to have but could ship in future release